Bovey Parish Neighbourhood Plan

Minutes of the 11th Steering Group Meeting

11th October 2018 at 7.00 pm

Attending:

Julie Arnold (JA)

Cllr Ulli Arnold (UA)

Mark Bailey (MB)

Cllr Janet Blair (JB)

Cllr Martyn Evans (ME)

Martin Iles (MI)

Cllr Eoghan Kelly (EK) - Chair

Cllr Steven Leigh (SL)

Amber MacDonald (AM)

Tom Wilson (TW)

Lisa Robillard Webb – Minute-taker

- Apologies: Marion Edwards (MED)

- Declaration of Interests: – None declared

- 3.1 Review of Minutes of the Previous Meeting (06/09/2018) – Minutes agreed after amendment of 13 pt 14.c ‘lead group’ to ‘group lead’.

3.2 Review of Actions:

  - Incomplete - Working Group volunteers in Land & Environment and Business & Employment to complete and hand in Declaration of Interests

  - Incomplete - EK to create a calendar of events for promotion of the NP

  - Draft completed but not finalised yet - EK (& JB) to produce an outline for Section 1 (could use version in Community Questionnaire Report) by October’s meeting

  - Completed - MI to contact Alexis at TDC to turn the promotional text for consultation events into display materials once consultation dates agreed. Additional deadline of 16 October 2018 - TW will meet with Simon (TDC) on presentation of information

  - Incomplete - UA tell ME of any agricultural land ownership he is aware of

  - Information requested, Mark Wells to complete if received - EK to ask Sibelco to provide a map of land they own

  - TDC recommended against this action due to raised expectations - ME to collate a list of the land within the ward with a future possibility of development.  The Land & Environment Working Group will contact Landowners, if appropriate

  - Completed - MED to amend the project plan with the consultation event dates once agreed.  On the Proposal paper, change the word ‘endorsement’ to ‘approval’ on pt 1.

  - Completed - MB book venues for consultation events

  - Completed – quote will be dependent on number of respondents - MED to ask Mark Wells to gain a quote from Devon Communities Together (DCT) on collating the results of the consultation feedback sheets

  - Completed - JB, MED & UA to present a completed draft of the Vision by 4th October Meeting

  - Completed – no response from members so no further action required - TW collate comments on AECOM’s document and facilitate a decision via e mail

  - Completed – no change - ME to circulate financial summary to the Group

  - Ongoing - All working groups to:

    - Circulate their minutes prior to group meetings

    - Reading each other’s minutes to avoid duplication

    - Always alert the group lead when undertaking a task central to their aims.

    - Seek more volunteers, if necessary

    - Remind volunteers to treat any working groups minutes as confidential

    - Bring draft objectives along to the 4th October 2018 Group meeting.

  - All members to:

    - Status not discussed - Read and consider ’Consultation & Issues for the new Local Plan – Dartmoor National Park’ to see if relevant to the NPSG prior to October’s meeting

    - Status not discussed - Read Revised Proposed Vision Statement and send comments to JB before 4th October (request e mail version from JB, if required)

    - See 7 -Tell ME of any knowledge they have of any relevant land ownership with a future possibility of development

    - Completed, see 12 - All members agreed to read AECOM’s document and send comments to TW by 17 September 2018.

- 4.1 Chair Update: None given.

4.2 Vice Chair Update:  TW met with Simon Lawton at TDC to discuss promotional materials, drafts for the next draft of Bovey Tracey’s consultation available to review. NB Alexis has left her role as it was the end of a short-term contract.  Please liaise with David Kiernan in future.

- Draft Objectives:

6.1 Discuss & agree DRAFT Objectives - Group discussed the advantages and disadvantages of:

- merging objectives down to a smaller number

- identifying draft objectives that may become policies

Group agreed for this meeting that they would discuss the draft objectives as circulated with the agenda. The public consultation will give necessary feedback for further changes.  Alexis advised to go with the draft objectives currently created.  In her absence had suggested that the title ‘Evidence/Justification/Background’ be replaced with ‘Context’ – group agreed with this change.

Agreed Wording Changes:

OBJECTIVE 1 (No change)

To ensure that everyone has access to housing that is both affordable and suited to the needs of differing age groups and backgrounds. This to include suitable provision within new developments to accommodate, in comfort, both elderly and disabled residents in a manner that provides easy access to the town’s facilities.

OBJECTIVE 2 (‘town’ to ‘Parish’)
To ensure that new housing developments are committed to providing sufficient green and community spaces within the development area to encourage engagement between residents and to enhance the rural feel and appearance of the Parish.

OBJECTIVE 3
To ensure that nature-rich areas are protected within and between developments.

OBJECTIVE 4 (‘boxes’ to ‘containers’)

For all plans of new build houses to include adequate storage provision for refuse containers and cycles, thus encouraging the use of cycleways and footpaths without encumbrance.

OBJECTIVE 5 (‘developers who commit to adhering’ to ‘development that adheres to’)

To support development that adheres to government and public preference for housing that is sustainable to build and financially efficient to run.

OBJECTIVE 6 (‘from development’ deleted)

To protect areas of environmental and community importance.

OBJECTIVE 7 (No change)
To enable resilience to climate change through the protection of the natural environment and the promotion of sustainable urban design.

OBJECTIVE 8 (No change)

To protect and enhance the natural environment to ensure no net loss of priority habitat and species.

OBJECTIVE 9 (No change)
To improve movement and road safety within the parish by reducing road traffic congestion, controlling traffic speed and enhancing alternatives to private car use (e.g. public transport, cycling and walking).

OBJECTIVE 10 (‘residential’ deleted)
To improve car parking arrangements to support high street business viability and to  enhance the street environment for local residents.

OBJECTIVE 11 (No change)

To support the extension of the existing healthcare facilities in Bovey Tracey Parish, and the building of new facilities if required.

OBJECTIVE 12 (‘on land allocated in the TDC Local Plan at BT4 or elsewhere,’ deleted)
To support an urgent replacement of the Bovey Tracey Primary School to meet the present and projected needs of a growing population.

OBJECTIVE 13. (Remove to ‘Policy’) 
To explore the long-term viability of secondary education facilities within Bovey Tracey Parish, to meet the present and projected needs of a growing population.

OBJECTIVE 14 (Now 13 – No Change)

To support the provision of a multi-use community facility offering space for sports, performance, and large community gatherings.

OBJECTIVE 15 (Now 14 – delete ‘through planning agreements and exploring cooperation with community groups and trusts’) (Remove to ‘Policy’)

To seek ways to improve investment in community places and spaces.

OBJECTIVE 16 (Now 15. – No Change)

To support the growth of a wider range of retail shops in the parish.

OBJECTIVE 17 (Now 16. – No Change)

To encourage the growth of a wide range of employment opportunities in the parish with particular emphasis on highly paid “hi tech”, manufacturing or professional opportunities.

- Community Engagement:

6.1 Discuss & agree arrangements for the 2nd engagement – Group agreed to the dates and times on the draft promotional material.  More volunteers needed for the meetings. November’s meeting will discuss the material to be presented / displayed at the consultation meetings.  Volunteers to be briefed on arrival.  Each meeting to have a key coordinator:

- TW first meeting

- AM for BTPS meeting

- UA/JA at the Distillery

- MB  - St Catherine’s, Heathfield

- EK/ME – Heathfield Community Centre

MB to e mail key coordinators with the relevant venue contact details.

- Date of Next Meeting:  Thursday 1st November 2018 at 7pm.

- AOB: TW alerted group to training ‘Neighbourhood Planning – Policy Writing’, Exeter by Devon Communities Together 2018, 10.00am – 1.30pm.  Please see DCT website.

- Summary of Actions:

  - EK (& JB) - Finalise draft outline for Section 1 (could use version in Community Questionnaire Report) by November’s meeting

  - EK to ask Mark Wells if Sibelco have provided a map of the land they own

  - MED - Change title ‘Evidence/Justification/Background’ be replaced with ‘Context’

  - TW – Give agreed changes to draft objectives to Simon at TDC for the preparation of consultation materials for events

  - MB -  E mail key coordinators with the relevant venue contact details for consultation events

  - All members to:

    - Prepare for and attend the diarised consultation events